## Estimates
Sr.No. | Function | Point Of Contact/Team
1 | Authentication & Authorization Management(operator,Maintenance,User) | Mahadevi Biradar,Satyajeet Deshmukh
2 | UI Panels for Mission Planning -DSM Maps,Map Data Preparation -DSM ,Survey Of India | Mahadevi Biradar,Satyajeet Deshmukh
3 | Data Exchange between GCS and GDT – RF | Mahadevi Biradar,Satyajeet Deshmukh
4 | UI Panels for GCS Operations-list down the appropriate mission parameters | Mahadevi Biradar,Satyajeet Deshmukh
5 | Notification Messages- health threshold,input on Emergency management procedure
6 | Communication & Networking Protocols-Commands List
7 | Alert Pop-Ups- health threshold,criteria for non-feasible mission plan,object detection requirement in video | Mahadevi Biradar,Satyajeet Deshmukh
8 | Data Storage & Back Up | Mahadevi Biradar,Satyajeet Deshmukh
9 | Video Recording / Image Snapshot storage | Mahadevi Biradar,Satyajeet Deshmukh
10 | System Health Assessment (Diagnostics Management) | Mahadevi Biradar,Satyajeet Deshmukh
11 | Fault Management-Fault Management and Fault Prioritization based on Severity,Diagnostics data | Mahadevi Biradar,Satyajeet Deshmukh
12 | Emergency Management System-wind sensors integration,Minors Fault,Rule based Emergency Procedure | Mahadevi Biradar,Satyajeet Deshmukh
13 | Alerts and Notification Management-Fault notification, Alerts,Emergency Action/Procedure,Camera & Night vision and Day vision object detection | Mahadevi Biradar,Satyajeet Deshmukh
14 | Video Processing at GCS | Mahadevi Biradar,Satyajeet Deshmukh
15 | Pre-& Post Test of all the Peripherals for UGV Systems-PTZ Cameras,Motor & Its Parameters,Battery,GNSS | Mahadevi Biradar,Satyajeet Deshmukh
16 | GO / NO GO decision -POST related requirements.(Payload- IRM, Motor, Engine Parameters & Other Parameters)-Pre & Post Test | Mahadevi Biradar,Satyajeet Deshmukh
17 | Return to Home-Upon System failures,Safety Return scenarios | Mahadevi Biradar,Satyajeet Deshmukh
Firmware Development
1 | Mode Selection(CRC,TeleOperation,Autonomous,Follow Me),all mode status check | Sachin Kate,Mahadevi Biradar
2 | Communucation & Networking -server creation ,connection established,process text message,send messages to clients,stop connection,check gps data(heading & location loss & update-update bms data,update ugv location,update counter) | Sachin Kate,Mahadevi Biradar
3 | connect to GPS,Get GPS Status-Stop -Request For Interruption ,update gps latitude and longitude | Sachin Kate,Mahadevi Biradar
4 | LMS Read-Connect,Get LMS Status,Stop LMS-Interruption & Stream Close | Sachin Kate,Mahadevi Biradar
5 | GamepadControls-Palco-Connect,Disconnect,Move While Stop ,Frame & Its Parameters,Command Codes,Payload Bytes,Checksum | Sachin Kate,Mahadevi Biradar
6 | Follow Me-UWB Anchor & Tags | Sachin Kate,Mahadevi Biradar
7 | Update Satellite Number | Sachin Kate,Mahadevi Biradar
8 | LMS-Check ,Connect,Get KMS StatusUpdate LMS Data,Handle GCS command ,Object Identification-Find Closest Obstacle-Find Obstacle in FOV,Error in autonomy | Sachin Kate,Mahadevi Biradar
9 | Handle Motor Driver Control | Sachin Kate,Mahadevi Biradar
10 | Handle PTZ Camera & 6+ 1 Cameras (move camera Up,Down,Right,Left) | Sachin Kate,Mahadevi Biradar
11 | Curtis Control & its Parameter | Sachin Kate,Mahadevi Biradar
12 | Autonomy-Calculate Distance,find closest obstacle | Sachin Kate,Mahadevi Biradar
13 | Can Communication Establishment-Motor Controls-Reconnect CAN,Drive Forward,Change Interlock Status,Turn Sharp Right,Left,Stop UGV | Sachin Kate,Mahadevi Biradar
Sr.No. | Peripheral Devices -Task | Point Of Contact/Team
1 | Joysticks Technical data Study | Mahadevi Biradar,Sachin Kate
2 | Trial Code for joysticks | Mahadevi Biradar,Sachin Kate
3 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
4 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
5 | Final Code | Mahadevi Biradar,Sachin Kate
6 | Camera Encoder Technical data Study | Mahadevi Biradar,Sachin Kate
7 | Trial Code for Camera Encoder | Mahadevi Biradar,Sachin Kate
8 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
9 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
10 | Final Code | Mahadevi Biradar,Sachin Kate
11 | PTZ Camera Technical data Study | Mahadevi Biradar,Sachin Kate
12 | Trial Code for PTZ Camera | Mahadevi Biradar,Sachin Kate
13 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
14 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
15 | Final Code | Mahadevi Biradar,Sachin Kate
16 | Adam Module Technical data Study | Mahadevi Biradar,Sachin Kate
17 | Trial Code for Adam Module | Mahadevi Biradar,Sachin Kate
18 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
19 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
20 | Final Code | Mahadevi Biradar,Sachin Kate
21 | GPS Technical data Study | Mahadevi Biradar,Sachin Kate
22 | Trial Code for GPS Module | Mahadevi Biradar,Sachin Kate
23 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
24 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
25 | Final Code | Mahadevi Biradar,Sachin Kate
26 | GNSS Technical data Study | Mahadevi Biradar,Sachin Kate
27 | Trial Code for GNSS Module | Mahadevi Biradar,Sachin Kate
28 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
29 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
30 | Final Code | Mahadevi Biradar,Sachin Kate
31 | Motor Technical data Study | Mahadevi Biradar,Sachin Kate
32 | Motor Driver Technical data Study | Mahadevi Biradar,Sachin Kate
33 | Trial Code for Motor Driver | Mahadevi Biradar,Sachin Kate
34 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
35 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
36 | Final Code | Mahadevi Biradar,Sachin Kate
37 | Camera Technical data Study | Mahadevi Biradar,Sachin Kate
38 | Trial Code for Camera Module | Mahadevi Biradar,Sachin Kate
39 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
40 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
41 | Final Code | Mahadevi Biradar,Sachin Kate
42 | Radio Technical data Study | Mahadevi Biradar,Sachin Kate
43 | Trial Code for Radio Module | Mahadevi Biradar,Sachin Kate
44 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
45 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
46 | Final Code | Mahadevi Biradar,Sachin Kate
47 | 3D LIDAR Technical data Study | Mahadevi Biradar,Sachin Kate
48 | Trial Code for 3D LIDAR | Mahadevi Biradar,Sachin Kate
49 | Code as per IEEE Standard | Mahadevi Biradar,Sachin Kate
50 | Code as per ROS2 | Mahadevi Biradar,Sachin Kate
51 | Final Code | Mahadevi Biradar,Sachin Kate
52 | Each Module Testing | Mahadevi Biradar,Sachin Kate
53 | All Module integartion | Mahadevi Biradar,Sachin Kate
54 | Final Code | Mahadevi Biradar,Sachin Kate
55 | Field Test | Mahadevi Biradar,Sachin Kate

## Standards
| IEEE-1012 – Software Standard for Verification and Validation | IEEE-12207- System and Software Engineering Life cycle Process
Clause Number | Standards to be tested | Clause Number | Process Name
5.1.1 | Management of V&V Activity | 6 | System Life Cycle Processes
| Software Verification and Validation plan Generation | 6.1 | Agreement Processes
| Baseline Change Management | 6.1.1 | Acquisition Process
| Management review of V&V | 6.1.2 | Supply Process
| Management and Technical Review support | 6.2 | Organizational Project-Enabling
| Interface with organisational and support process | 6.2.1 | Life Cycle Model Management Process
|  | 6.2.2 | Infrastructure Management Process
5.2.1 | Acquistion support V&V Activity | 6.2.3 | Project Portfolio Management Process
| Scoping the V&V Effort | 6.2.4 | Human Resource Management Process
| Planning the Interface between V&V Effort and Supplier | 6.2.5 | Quality Management Process
| System Requirement Review | 6.3 | Project Processes
|  | 6.3.1 | Project Planning Process
5.3.1 | Planning V&V Activity | 6.3.2 | Project Assessment and Control Process
| Planning the Interface between V&V Effort and Supplier | 6.3.3 | Decision Management Process
| Contract Verification | 6.3.4 | Risk Management Process
|  | 6.3.5 | Configuration Management Process
5.4.1 | Concept V&V Activity | 6.3.6 | Information Management Process
| Concept Documentation Evaluation | 6.3.7 | Measurement Process
| Criticality Analysis | 6.4 | Technical Processes
| Hardware/Software User Requirements | 6.4.1 | Stakeholder Requirements Definition
| Traceability Analysis | 6.4.2 | System Requirements Analysis
| Hazard Analysis | 6.4.3 | System Architectural Design
| Risk Analysis | 6.4.4 | Implementation Process
|  | 6.4.5 | System Integration Process
5.4.2 | Requirement V&V Activity | 6.4.6 | System Qualification Testing Process
| Traceability Analysis | 6.4.7 | Software Installation
| Software Requirements Evaluation | 6.4.8 | Software Acceptance Support
| Interface Analysis | 6.4.9 | Software Operation Process
| Criticality Analysis | 6.4.10 | Software Maintenance Process
| System V&V Test Plan | 6.4.11 | Software Disposal Process
| Acceptance V&V Test Plan Generation and Verification | 7 | Software Life Cycle Processes
| Configuration Management Assessment | 7.1 | Software Implementation Processes
| Hazard Analysis | 7.1.1 | Software Implementation Process
| Risk Analysis | 7.1.2 | Software Requirements Analysis Process
|  | 7.1.3 | Software Architectural Design Process
5.4.3 | Design V&V Activity | 7.1.4 | Software Detailed Design Process
| Traceability Analysis | 7.1.5 | Software Construction Process
| Software Design Evaluation | 7.1.6 | Software Integration Process
| Interface Analysis | 7.1.7 | Software Qualification Testing Process
| Criticality Analysis | 7.2 | Software Support Processes
| Component V&V test plan Generation and Verification | 7.2.1 | Software Documentation Management
| Integration V&V Test Plan Generation and Verification | 7.2.2 | Software Configuration Management
| V&V Test Design Generation and Verification | 7.2.3 | Software Quality Assurance Process
| Hazard Analysis | 7.2.4 | Software Verification Process
| Risk Analysis | 7.2.5 | Software Validation Process
|  | 7.2.6 | Software Review Process
5.4.4 | Implementation V&V Activity | 7.2.7 | Software Audit Process
| Traceability Analysis | 7.2.8 | Software Problem Resolution Process
| Source Code and Source Code Documentation Evaluation | 7.3 | Software Reuse Processes
| Interface Analysis | 7.3.1 | Domain Engineering Process
| Criticality Analysis | 7.3.2 | Reuse Asset Management Process
| V&V Test case Generation and Verification | 7.3.3 | Reuse Program Management Process
V&V Test Procedure Generation and Verification
Component V&V test execution and Verification
Hazard Analysis
Risk Analysis
5.4.5 | Test V&V Activity
Traceability Analysis
Acceptance V&V Test Procedure Generation and Verification
Integration V&V test Execution and Verification
System V&V Test Execution and Verification
Acceptance V&V Test Execution and Verification
Hazard Analysis
Risk Analysis
5.4.6 | Installation and Chechout V&V Activity
Installation Configuration Audit
Installation checkout
Hazard Analysis
Risk Analysis
V&V Final Report Generation