## Sheet1
Module | Submodule | Task | Start Date | End Date | Phase | Duration (days) | Status | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | Description / Key Activities
Firmware Development | Boot & BSP | Bootloader | 2025-11-01 | 2025-12-01 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Boot & BSP | MCU bring-up | 2025-11-11 | 2025-12-11 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Boot & BSP | RTOS config | 2025-11-21 | 2025-12-21 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Drivers | IMU driver | 2025-12-01 | 2025-12-31 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Drivers | GNSS driver | 2025-12-11 | 2026-01-10 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Drivers | Camera driver | 2025-12-21 | 2026-01-20 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Control | Motor control | 2025-12-31 | 2026-01-30 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Control | Power management | 2026-01-10 | 2026-02-09 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Control | Failsafe logic | 2026-01-20 | 2026-02-19 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Comm | CAN interface | 2026-01-30 | 2026-03-01 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Comm | UART telemetry | 2026-02-09 | 2026-03-11 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Firmware Development | Comm | Radio protocol | 2026-02-19 | 2026-03-21 | Design/Dev/Test | 30 | Planned | [6 empty] | Define firmware architecture and hardware interface requirements.
Hardware & Peripheral Testing | Test Setup | Bench setup | 2025-11-15 | 2025-12-05 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Test Setup | Power test | 2025-11-27 | 2025-12-17 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Test Setup | Sensor calibration | 2025-12-09 | 2025-12-29 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Peripherals | Camera DRI tests | 2025-12-21 | 2026-01-10 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Peripherals | LiDAR integration | 2026-01-02 | 2026-01-22 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Peripherals | Gimbal tests | 2026-01-14 | 2026-02-03 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Environmental | Thermal test | 2026-01-26 | 2026-02-15 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Environmental | Vibration test | 2026-02-07 | 2026-02-27 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Hardware & Peripheral Testing | Environmental | EMI pre-checks | 2026-02-19 | 2026-03-11 | Validation | 20 | Planned | [6 empty] | Perform EMI/EMC, vibration, and thermal tests on integrated electronics.
Quality Assurance (QA) | Planning | Test plan | 2025-11-21 | 2025-12-16 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Quality Assurance (QA) | Planning | Test cases | 2025-12-05 | 2025-12-30 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Quality Assurance (QA) | Execution | Functional tests | 2025-12-19 | 2026-01-13 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Quality Assurance (QA) | Execution | Regression tests | 2026-01-02 | 2026-01-27 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Quality Assurance (QA) | Reporting | Bug triage | 2026-01-16 | 2026-02-10 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Quality Assurance (QA) | Reporting | Verification | 2026-01-30 | 2026-02-24 | QA | 25 | Planned | [6 empty] | Track issues, perform validation cycles, and ensure defect closure.
Project Management (PMO) | Governance | Kickoff, documentation | 2025-11-01 | 2025-12-11 | PMO | 40 | Planned | [6 empty] | Manage team coordination, progress tracking, and reporting.
Project Management (PMO) | Tracking | Weekly status, risk register | 2025-12-01 | 2026-01-10 | PMO | 40 | Planned | [6 empty] | Manage team coordination, progress tracking, and reporting.
Project Management (PMO) | Handover | Training, delivery | 2025-12-31 | 2026-02-09 | PMO | 40 | Planned | [6 empty] | Manage team coordination, progress tracking, and reporting.
GUI / Frontend Development | GCS Interface Module | Authentication & Authorization Management | 2025-11-01 | 2025-11-21 | Phase 1 - Design | 20 | Planned | [6 empty] | Implement role-based access for operator, maintenance, and user accounts.
GUI / Frontend Development | GCS Interface Module | UI Panels for Mission Planning - DSM Maps, Map Data Preparation - DSM, Survey Of India | 2025-11-11 | 2025-12-01 | Phase 1 - Design | 20 | Planned | [6 empty] | Design mission planning UI using DSM maps and Survey of India datasets.
GUI / Frontend Development | GCS Interface Module | Data Exchange between GCS and GDT – RF | 2025-11-21 | 2025-12-11 | Phase 1 - Design | 20 | Planned | [6 empty] | Establish reliable RF-based data exchange between GCS and ground terminal.
GUI / Frontend Development | GCS Interface Module | UI Panels for GCS Operations - Mission Parameters | 2025-12-01 | 2025-12-21 | Phase 2 - Development | 20 | Planned | [6 empty] | Develop UI panels to list and configure mission parameters for UGV control.
GUI / Frontend Development | GCS Interface Module | Notification Messages - Health Threshold & Emergency | 2025-12-11 | 2025-12-31 | Phase 2 - Development | 20 | Planned | [6 empty] | Implement notification system for health status and emergency inputs.
GUI / Frontend Development | GCS Interface Module | Communication & Networking Protocols - Commands List | 2025-12-21 | 2026-01-10 | Phase 2 - Development | 20 | Planned | [6 empty] | Define and integrate command sets for communication and networking control.
GUI / Frontend Development | GCS Interface Module | Alert Pop-Ups - Non-feasible Plan & Object Detection | 2025-12-31 | 2026-01-20 | Phase 3 - Integration | 20 | Planned | [6 empty] | Develop alert system for health threshold breaches and mission feasibility checks.
GUI / Frontend Development | GCS Interface Module | Data Storage & Back Up | 2026-01-10 | 2026-01-30 | Phase 3 - Integration | 20 | Planned | [6 empty] | Set up secure data storage and automated backup mechanisms.
GUI / Frontend Development | GCS Interface Module | Video Recording / Image Snapshot Storage | 2026-01-20 | 2026-02-09 | Phase 3 - Integration | 20 | Planned | [6 empty] | Enable video recording and image capture with timestamp metadata.
GUI / Frontend Development | GCS Interface Module | System Health Assessment (Diagnostics Management) | 2026-01-30 | 2026-02-19 | Phase 4 - Validation | 20 | Planned | [6 empty] | Develop diagnostics tools for continuous system health monitoring.
GUI / Frontend Development | GCS Interface Module | Fault Management - Severity Prioritization | 2026-02-09 | 2026-03-01 | Phase 4 - Validation | 20 | Planned | [6 empty] | Implement rule-based fault detection, classification, and prioritization system.
GUI / Frontend Development | GCS Interface Module | Emergency Management System | 2026-02-19 | 2026-03-11 | Phase 4 - Validation | 20 | Planned | [6 empty] | Integrate wind sensors and automate rule-based emergency procedures.
GUI / Frontend Development | GCS Interface Module | Alerts and Notification Management | 2026-03-01 | 2026-03-21 | Phase 5 - Testing | 20 | Planned | [6 empty] | Create alert system for faults, emergencies, and visual detection from cameras.
GUI / Frontend Development | GCS Interface Module | Video Processing at GCS | 2026-03-11 | 2026-03-31 | Phase 5 - Testing | 20 | Planned | [6 empty] | Implement video decoding, enhancement, and real-time processing pipeline.
GUI / Frontend Development | GCS Interface Module | Pre & Post Test of all Peripherals | 2026-03-21 | 2026-04-10 | Phase 5 - Testing | 20 | Planned | [6 empty] | Perform pre/post validation of UGV peripherals including PTZ, battery, GNSS.
GUI / Frontend Development | GCS Interface Module | GO / NO GO Decision - POST | 2026-03-31 | 2026-04-20 | Phase 6 - Delivery | 20 | Planned | [6 empty] | Automate system health evaluation and decision logic for mission readiness.
GUI / Frontend Development | GCS Interface Module | Return to Home - System Failures | 2026-04-10 | 2026-04-30 | Phase 6 - Delivery | 20 | Planned | [6 empty] | Implement safety return protocol upon system failure or critical fault detection.