## Project_Timeline
Module | Submodule | Task | Team Involved | Start Date | End Date | Phase | Duration (days) | Status | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026
GUI / Frontend Development | UI/UX | Wireframes | GUI / Frontend Development | 2025-11-01 | 2025-11-29 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | UI/UX | Prototype | GUI / Frontend Development | 2025-11-08 | 2025-12-06 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | UI/UX | Accessibility review | GUI / Frontend Development | 2025-11-15 | 2025-12-13 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Dashboard | Telemetry widgets | GUI / Frontend Development | 2025-11-22 | 2025-12-20 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Dashboard | Map integration | GUI / Frontend Development | 2025-11-29 | 2025-12-27 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Dashboard | Control widgets | GUI / Frontend Development | 2025-12-06 | 2026-01-03 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Controls | Command panel | GUI / Frontend Development | 2025-12-13 | 2026-01-10 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Controls | Payload controls | GUI / Frontend Development | 2025-12-20 | 2026-01-17 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Controls | Mode switcher | GUI / Frontend Development | 2025-12-27 | 2026-01-24 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Integration | API contracts | GUI / Frontend Development | 2026-01-03 | 2026-01-31 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Integration | Auth & Security | GUI / Frontend Development | 2026-01-10 | 2026-02-07 | Design/Dev/Test | 28 | Planned
GUI / Frontend Development | Integration | Data logging | GUI / Frontend Development | 2026-01-17 | 2026-02-14 | Design/Dev/Test | 28 | Planned
Firmware Development | Boot & BSP | Bootloader | Firmware Development | 2025-11-01 | 2025-12-01 | Design/Dev/Test | 30 | Planned
Firmware Development | Boot & BSP | MCU bring-up | Firmware Development | 2025-11-11 | 2025-12-11 | Design/Dev/Test | 30 | Planned
Firmware Development | Boot & BSP | RTOS config | Firmware Development | 2025-11-21 | 2025-12-21 | Design/Dev/Test | 30 | Planned
Firmware Development | Drivers | IMU driver | Firmware Development | 2025-12-01 | 2025-12-31 | Design/Dev/Test | 30 | Planned
Firmware Development | Drivers | GNSS driver | Firmware Development | 2025-12-11 | 2026-01-10 | Design/Dev/Test | 30 | Planned
Firmware Development | Drivers | Camera driver | Firmware Development | 2025-12-21 | 2026-01-20 | Design/Dev/Test | 30 | Planned
Firmware Development | Control | Motor control | Firmware Development | 2025-12-31 | 2026-01-30 | Design/Dev/Test | 30 | Planned
Firmware Development | Control | Power management | Firmware Development | 2026-01-10 | 2026-02-09 | Design/Dev/Test | 30 | Planned
Firmware Development | Control | Failsafe logic | Firmware Development | 2026-01-20 | 2026-02-19 | Design/Dev/Test | 30 | Planned
Firmware Development | Comm | CAN interface | Firmware Development | 2026-01-30 | 2026-03-01 | Design/Dev/Test | 30 | Planned
Firmware Development | Comm | UART telemetry | Firmware Development | 2026-02-09 | 2026-03-11 | Design/Dev/Test | 30 | Planned
Firmware Development | Comm | Radio protocol | Firmware Development | 2026-02-19 | 2026-03-21 | Design/Dev/Test | 30 | Planned
Hardware & Peripheral Testing | Test Setup | Bench setup | Hardware & Peripheral Testing | 2025-11-15 | 2025-12-05 | Validation | 20 | Planned
Hardware & Peripheral Testing | Test Setup | Power test | Hardware & Peripheral Testing | 2025-11-27 | 2025-12-17 | Validation | 20 | Planned
Hardware & Peripheral Testing | Test Setup | Sensor calibration | Hardware & Peripheral Testing | 2025-12-09 | 2025-12-29 | Validation | 20 | Planned
Hardware & Peripheral Testing | Peripherals | Camera DRI tests | Hardware & Peripheral Testing | 2025-12-21 | 2026-01-10 | Validation | 20 | Planned
Hardware & Peripheral Testing | Peripherals | LiDAR integration | Hardware & Peripheral Testing | 2026-01-02 | 2026-01-22 | Validation | 20 | Planned
Hardware & Peripheral Testing | Peripherals | Gimbal tests | Hardware & Peripheral Testing | 2026-01-14 | 2026-02-03 | Validation | 20 | Planned
Hardware & Peripheral Testing | Environmental | Thermal test | Hardware & Peripheral Testing | 2026-01-26 | 2026-02-15 | Validation | 20 | Planned
Hardware & Peripheral Testing | Environmental | Vibration test | Hardware & Peripheral Testing | 2026-02-07 | 2026-02-27 | Validation | 20 | Planned
Hardware & Peripheral Testing | Environmental | EMI pre-checks | Hardware & Peripheral Testing | 2026-02-19 | 2026-03-11 | Validation | 20 | Planned
Quality Assurance (QA) | Planning | Test plan | Quality Assurance (QA) | 2025-11-21 | 2025-12-16 | QA | 25 | Planned
Quality Assurance (QA) | Planning | Test cases | Quality Assurance (QA) | 2025-12-05 | 2025-12-30 | QA | 25 | Planned
Quality Assurance (QA) | Execution | Functional tests | Quality Assurance (QA) | 2025-12-19 | 2026-01-13 | QA | 25 | Planned
Quality Assurance (QA) | Execution | Regression tests | Quality Assurance (QA) | 2026-01-02 | 2026-01-27 | QA | 25 | Planned
Quality Assurance (QA) | Reporting | Bug triage | Quality Assurance (QA) | 2026-01-16 | 2026-02-10 | QA | 25 | Planned
Quality Assurance (QA) | Reporting | Verification | Quality Assurance (QA) | 2026-01-30 | 2026-02-24 | QA | 25 | Planned
Project Management (PMO) | Governance | Kickoff, documentation | Project Management (PMO) | 2025-11-01 | 2025-12-11 | PMO | 40 | Planned
Project Management (PMO) | Tracking | Weekly status, risk register | Project Management (PMO) | 2025-12-01 | 2026-01-10 | PMO | 40 | Planned
Project Management (PMO) | Handover | Training, delivery | Project Management (PMO) | 2025-12-31 | 2026-02-09 | PMO | 40 | Planned