## Sheet1
Module | Task | Team Involved | Start Date | End Date | Phase | Status
GUI / Frontend Development | UI Wireframes & Design Finalization | GUI / Frontend Development | 2025-11-01 | 2025-11-30 | Phase 1 - Design | Planned
GUI / Frontend Development | Frontend Framework Setup (React / Qt) | GUI / Frontend Development | 2025-12-01 | 2025-12-31 | Phase 2 - Setup | Planned
GUI / Frontend Development | Core UI Implementation (Dashboard, Controls) | GUI / Frontend Development | 2026-01-01 | 2026-01-31 | Phase 3 - Development | Planned
GUI / Frontend Development | Integration with Backend APIs | GUI / Frontend Development | 2026-02-01 | 2026-02-28 | Phase 4 - Integration | Planned
GUI / Frontend Development | User Testing & UI Optimization | GUI / Frontend Development | 2026-03-01 | 2026-03-31 | Phase 5 - Testing | Planned
GUI / Frontend Development | Final Review & Delivery | GUI / Frontend Development | 2026-04-01 | 2026-04-30 | Phase 6 - Delivery | Planned
Firmware Development | System Requirements & Architecture | Firmware Development | 2025-11-01 | 2025-11-30 | Phase 1 - Design | Planned
Firmware Development | Microcontroller Board Bring-up | Firmware Development | 2025-12-01 | 2025-12-31 | Phase 2 - Setup | Planned
Firmware Development | Core Control Logic & Sensor Drivers | Firmware Development | 2026-01-01 | 2026-01-31 | Phase 3 - Development | Planned
Firmware Development | Peripheral Communication (CAN, UART, SPI) | Firmware Development | 2026-02-01 | 2026-02-28 | Phase 4 - Integration | Planned
Firmware Development | Firmware Validation & Debugging | Firmware Development | 2026-03-01 | 2026-03-31 | Phase 5 - Testing | Planned
Firmware Development | Release Build & Documentation | Firmware Development | 2026-04-01 | 2026-04-30 | Phase 6 - Delivery | Planned
Hardware & Peripheral Testing | Hardware Test Bench Setup | Hardware & Peripheral Testing | 2025-11-15 | 2025-12-15 | Phase 1 - Setup | Planned
Hardware & Peripheral Testing | Peripheral Interface Validation | Hardware & Peripheral Testing | 2026-01-01 | 2026-01-31 | Phase 2 - Validation | Planned
Hardware & Peripheral Testing | Environmental & Stress Testing | Hardware & Peripheral Testing | 2026-02-01 | 2026-02-28 | Phase 3 - Testing | Planned
Hardware & Peripheral Testing | Integration with Firmware | Hardware & Peripheral Testing | 2026-03-01 | 2026-03-31 | Phase 4 - Integration | Planned
Hardware & Peripheral Testing | Final Validation Report | Hardware & Peripheral Testing | 2026-04-01 | 2026-04-15 | Phase 5 - Delivery | Planned
Quality Assurance (QA) | Test Plan Preparation | QA | 2025-11-15 | 2025-12-15 | Phase 1 - Planning | Planned
Quality Assurance (QA) | Functional & Regression Testing | QA | 2026-01-01 | 2026-02-28 | Phase 2 - Execution | Planned
Quality Assurance (QA) | Bug Tracking & Resolution | QA | 2026-03-01 | 2026-03-31 | Phase 3 - Validation | Planned
Quality Assurance (QA) | Final QA Sign-off | QA | 2026-04-01 | 2026-04-15 | Phase 4 - Delivery | Planned
Project Management (PMO) | Project Kickoff & Resource Allocation | PMO | 2025-11-01 | 2025-11-15 | Phase 1 - Planning | Planned
Project Management (PMO) | Weekly Progress Tracking | PMO | 2025-11-15 | 2026-04-30 | Ongoing | Planned
Project Management (PMO) | Mid-Project Review | PMO | 2026-02-01 | 2026-02-15 | Phase 3 - Review | Planned
Project Management (PMO) | Final Delivery Review | PMO | 2026-04-15 | 2026-04-30 | Phase 6 - Delivery | Planned