## Sheet1
Module | Submodule | Task | Team Involved | Start Date | End Date | Phase | Duration (days) | Sprint # | Status | Description / Key Activities
GUI / Frontend Development | GCS Interface Module | Authentication & Authorization Management | Frontend Team | 2025-11-01 | 2025-11-07 | Design/Development | 7 | Sprint 1 | Planned | Implement role-based access for operator, maintenance, and user accounts.
GUI / Frontend Development | GCS Interface Module | UI Panels for Mission Planning - DSM Maps | Frontend Team | 2025-11-08 | 2025-11-14 | Design/Development | 7 | Sprint 2 | Planned | Design mission planning UI using DSM maps and Survey of India datasets.
GUI / Frontend Development | GCS Interface Module | Data Exchange between GCS and GDT – RF | Frontend Team | 2025-11-15 | 2025-11-21 | Design/Development | 7 | Sprint 3 | Planned | Establish reliable RF-based data exchange between GCS and ground terminal.
GUI / Frontend Development | GCS Interface Module | Notification Messages - Health Threshold & Emergency | Frontend Team | 2025-11-22 | 2025-11-28 | Design/Development | 7 | Sprint 4 | Planned | Implement notification system for health status and emergency inputs.
GUI / Frontend Development | GCS Interface Module | Communication & Networking Protocols - Commands List | Frontend Team | 2025-11-29 | 2025-12-05 | Design/Development | 7 | Sprint 5 | Planned | Define and integrate command sets for communication and networking control.
GUI / Frontend Development | GCS Interface Module | Alert Pop-Ups - Non-feasible Plan & Object Detection | Frontend Team | 2025-12-06 | 2025-12-12 | Design/Development | 7 | Sprint 6 | Planned | Develop alert system for mission feasibility checks and object detection.
GUI / Frontend Development | GCS Interface Module | Data Storage & Back Up | Frontend Team | 2025-12-13 | 2025-12-19 | Design/Development | 7 | Sprint 7 | Planned | Set up secure data storage and automated backup mechanisms.
GUI / Frontend Development | GCS Interface Module | Video Recording / Image Snapshot Storage | Frontend Team | 2025-12-20 | 2025-12-26 | Design/Development | 7 | Sprint 8 | Planned | Enable video recording and image capture with timestamp metadata.
GUI / Frontend Development | GCS Interface Module | System Health Assessment (Diagnostics Management) | Frontend Team | 2025-12-27 | 2026-01-02 | Design/Development | 7 | Sprint 9 | Planned | Develop diagnostics tools for continuous system health monitoring.
GUI / Frontend Development | GCS Interface Module | Emergency Management System | Frontend Team | 2026-01-03 | 2026-01-09 | Design/Development | 7 | Sprint 10 | Planned | Integrate wind sensors and automate rule-based emergency procedures.
GUI / Frontend Development | GCS Interface Module | Alerts and Notification Management | Frontend Team | 2026-01-10 | 2026-01-16 | Design/Development | 7 | Sprint 11 | Planned | Create alert system for faults, emergencies, and visual detection from cameras.
GUI / Frontend Development | GCS Interface Module | Video Processing at GCS | Frontend Team | 2026-01-17 | 2026-01-23 | Design/Development | 7 | Sprint 12 | Planned | Implement video decoding, enhancement, and real-time processing pipeline.
GUI / Frontend Development | GCS Interface Module | GO / NO GO Decision - POST | Frontend Team | 2026-01-24 | 2026-01-30 | Design/Development | 7 | Sprint 13 | Planned | Automate system health evaluation and decision logic for mission readiness.
GUI / Frontend Development | GCS Interface Module | Return to Home - System Failures | Frontend Team | 2026-01-31 | 2026-02-06 | Design/Development | 7 | Sprint 14 | Planned | Implement safety return protocol upon system failure or critical fault detection.
Firmware Development | Firmware & Peripheral Integration | Mode Selection & Status Check | Sachin Kate, Mahadevi Biradar | 2025-11-29 | 2025-12-05 | Development/Integration | 7 | Sprint 5 | Planned | Develop and validate control modes: CRC, TeleOp, Autonomous, Follow Me.
Firmware Development | Firmware & Peripheral Integration | Communication & Networking | Sachin Kate, Mahadevi Biradar | 2025-12-06 | 2025-12-12 | Development/Integration | 7 | Sprint 6 | Planned | Build server-client communication, process GPS and telemetry data.
Firmware Development | Firmware & Peripheral Integration | GPS Connection & Updates | Sachin Kate, Mahadevi Biradar | 2025-12-13 | 2025-12-19 | Development/Integration | 7 | Sprint 7 | Planned | Integrate GPS data updates and handle interruptions gracefully.
Firmware Development | Firmware & Peripheral Integration | LMS Read/Status Management | Sachin Kate, Mahadevi Biradar | 2025-12-20 | 2025-12-26 | Development/Integration | 7 | Sprint 8 | Planned | Develop LMS data streaming, status read, and safe stop mechanism.
Firmware Development | Firmware & Peripheral Integration | Gamepad Controls | Sachin Kate, Mahadevi Biradar | 2025-12-27 | 2026-01-02 | Development/Integration | 7 | Sprint 9 | Planned | Integrate Palco gamepad, command codes, payload checksum validation.
Firmware Development | Firmware & Peripheral Integration | Follow Me - UWB Anchors | Sachin Kate, Mahadevi Biradar | 2026-01-03 | 2026-01-09 | Development/Integration | 7 | Sprint 10 | Planned | Implement UWB-based Follow-Me logic and testing.
Firmware Development | Firmware & Peripheral Integration | Handle Motor Driver Control | Sachin Kate, Mahadevi Biradar | 2026-01-10 | 2026-01-16 | Development/Integration | 7 | Sprint 11 | Planned | Develop control logic for UGV motor driver, interlocks, and speed control.
Firmware Development | Firmware & Peripheral Integration | Handle PTZ & 6+1 Cameras | Sachin Kate, Mahadevi Biradar | 2026-01-17 | 2026-01-23 | Development/Integration | 7 | Sprint 12 | Planned | Implement control for camera movement and switching.
Firmware Development | Firmware & Peripheral Integration | Curtis Control Parameters | Sachin Kate, Mahadevi Biradar | 2026-01-24 | 2026-01-30 | Development/Integration | 7 | Sprint 13 | Planned | Interface and calibrate Curtis control module.
Firmware Development | Firmware & Peripheral Integration | Autonomy - Obstacle Avoidance | Sachin Kate, Mahadevi Biradar | 2026-01-31 | 2026-02-06 | Development/Integration | 7 | Sprint 14 | Planned | Implement distance calculation and closest obstacle identification.
Firmware Development | Firmware & Peripheral Integration | CAN Communication Establishment | Sachin Kate, Mahadevi Biradar | 2026-02-07 | 2026-02-13 | Development/Integration | 7 | Sprint 15 | Planned | Establish CAN link for motor and peripheral control.
Firmware Development | Firmware & Peripheral Integration | Peripheral Device Integration | Sachin Kate, Mahadevi Biradar | 2026-02-14 | 2026-02-20 | Development/Integration | 7 | Sprint 16 | Planned | Integrate joystick, camera encoder, PTZ, GPS, GNSS, motor drivers, etc.
Firmware Development | Firmware & Peripheral Integration | Module Testing & Integration | Sachin Kate, Mahadevi Biradar | 2026-02-21 | 2026-02-27 | Development/Integration | 7 | Sprint 17 | Planned | Perform module-level testing and integration verification.
Firmware Development | Firmware & Peripheral Integration | Field Test & Validation | Sachin Kate, Mahadevi Biradar | 2026-02-28 | 2026-03-06 | Development/Integration | 7 | Sprint 18 | Planned | Conduct on-field validation and finalize firmware release.
Hardware & Peripheral Testing | Validation & Field Tests | Hardware Bench Setup | Hardware & QA Team | 2026-01-24 | 2026-01-30 | Validation/Testing | 7 | Sprint 13 | Planned | Prepare hardware test bench for calibration and environmental testing.
Hardware & Peripheral Testing | Validation & Field Tests | Sensor Calibration & Validation | Hardware & QA Team | 2026-01-31 | 2026-02-06 | Validation/Testing | 7 | Sprint 14 | Planned | Calibrate LiDAR, GPS, IMU sensors and validate accuracy.
Hardware & Peripheral Testing | Validation & Field Tests | EMI/EMC Testing | Hardware & QA Team | 2026-02-07 | 2026-02-13 | Validation/Testing | 7 | Sprint 15 | Planned | Perform EMI/EMC compliance tests per MIL-STD-461E/F.
Hardware & Peripheral Testing | Validation & Field Tests | Thermal & Vibration Testing | Hardware & QA Team | 2026-02-14 | 2026-02-20 | Validation/Testing | 7 | Sprint 16 | Planned | Conduct vibration and thermal stress testing for hardware durability.
Hardware & Peripheral Testing | Validation & Field Tests | Field Integration Testing | Hardware & QA Team | 2026-02-21 | 2026-02-27 | Validation/Testing | 7 | Sprint 17 | Planned | Execute full system integration and field testing with UGV.
Quality Assurance (QA) | Testing & Validation | QA Planning & Test Case Design | QA Team | 2026-02-21 | 2026-02-27 | Testing/Delivery | 7 | Sprint 17 | Planned | Define QA strategy, acceptance criteria, and detailed test cases.
Quality Assurance (QA) | Testing & Validation | Regression & Functional Testing | QA Team | 2026-02-28 | 2026-03-06 | Testing/Delivery | 7 | Sprint 18 | Planned | Execute regression tests and verify system functionality.
Quality Assurance (QA) | Testing & Validation | Integration Validation | QA Team | 2026-03-07 | 2026-03-13 | Testing/Delivery | 7 | Sprint 19 | Planned | Validate cross-module integration and report issues.
Quality Assurance (QA) | Testing & Validation | System Validation & Documentation | QA Team | 2026-03-14 | 2026-03-20 | Testing/Delivery | 7 | Sprint 20 | Planned | Finalize test reports, traceability matrix, and QA sign-off.
Project Management (PMO) | Management & Reviews | Project Kick-off & Resource Allocation | PMO Team | 2025-11-01 | 2025-11-21 | Continuous | 21 | Sprint 1 | Planned | Initialize project, define deliverables, and allocate resources.
Project Management (PMO) | Management & Reviews | Weekly Progress Reviews | PMO Team | 2025-12-13 | 2026-01-02 | Continuous | 21 | Sprint 7 | Planned | Monitor weekly sprint progress and risk tracking.
Project Management (PMO) | Management & Reviews | Mid-Project Review | PMO Team | 2026-01-24 | 2026-02-13 | Continuous | 21 | Sprint 13 | Planned | Assess progress at 3-month milestone and adjust schedule if needed.
Project Management (PMO) | Management & Reviews | Final Delivery & Documentation | PMO Team | 2026-03-07 | 2026-03-27 | Continuous | 21 | Sprint 19 | Planned | Compile all deliverables, close-out report, and handover.