## Sheet1
Module | Submodule | Task | Team Involved | Start Date | End Date | Phase | Duration (days) | Sprint # | Status | Description / Key Activities
GUI / Frontend Development
| GCS Interface Module | Authentication & Authorization Management | Frontend Team | 2025-11-01 | 2025-11-07 | Design/Development | 7 | Sprint 1 | Planned | Implement role-based access for operator, maintenance, and user accounts.
GUI / Frontend Development | GCS Interface Module | UI Panels for Mission Planning - DSM Maps,Map Data Preparation - DSM ,Survey Of India | Frontend Team | 2025-11-08 | 2025-11-14 | Design/Development | 7 | Sprint 2 | Planned | Design mission planning UI using DSM and Survey of India datasets; map data prep.
GUI / Frontend Development | GCS Interface Module | Data Exchange between GCS and GDT – RF | Frontend Team | 2025-11-15 | 2025-11-21 | Design/Development | 7 | Sprint 3 | Planned | Establish RF data exchange, reliable messaging and retries.
GUI / Frontend Development | GCS Interface Module | UI Panels for GCS Operations - Mission Parameters | Frontend Team | 2025-11-22 | 2025-11-28 | Design/Development | 7 | Sprint 4 | Planned | Develop panels to list/configure mission parameters.
GUI / Frontend Development | GCS Interface Module | Notification Messages- health threshold,input on Emergency management procedure | Frontend Team | 2025-11-29 | 2025-12-05 | Design/Development | 7 | Sprint 5 | Planned | Implement notifications for health thresholds and emergency inputs.
GUI / Frontend Development | GCS Interface Module | Communication & Networking Protocols-Commands List | Frontend Team | 2025-12-06 | 2025-12-12 | Design/Development | 7 | Sprint 6 | Planned | Define commands, message formats and networking protocols.
GUI / Frontend Development | GCS Interface Module | Alert Pop-Ups- health threshold,criteria for non-feasible mission plan,object detection requirement in video | Frontend Team | 2025-12-13 | 2025-12-19 | Design/Development | 7 | Sprint 7 | Planned | Alert system for thresholds, mission feasibility and object-detection triggers.
GUI / Frontend Development | GCS Interface Module | Data Storage & Back Up | Frontend Team | 2025-12-20 | 2025-12-26 | Design/Development | 7 | Sprint 8 | Planned | Implement secure storage, retention, and automated backups.
GUI / Frontend Development | GCS Interface Module | Video Recording / Image Snapshot storage | Frontend Team | 2025-12-27 | 2026-01-02 | Design/Development | 7 | Sprint 9 | Planned | Implement recording, snapshot, indexing and retrieval with timestamps.
GUI / Frontend Development | GCS Interface Module | System Health Assessment (Diagnostics Management) | Frontend Team | 2026-01-03 | 2026-01-09 | Design/Development | 7 | Sprint 10 | Planned | Continuous diagnostics, telemetry health scoring and reporting.
GUI / Frontend Development | GCS Interface Module | Fault Management-Fault Management and Fault Prioritization based on Severity,Diagnostics data | Frontend Team | 2026-01-10 | 2026-01-16 | Design/Development | 7 | Sprint 11 | Planned | Rule-based fault classification and prioritized handling.
GUI / Frontend Development | GCS Interface Module | Emergency Management System-wind sensors integration,Minors Fault,Rule based Emergency Procedure | Frontend Team | 2026-01-17 | 2026-01-23 | Design/Development | 7 | Sprint 12 | Planned | Integrate environment sensors and automated emergency rules.
GUI / Frontend Development | GCS Interface Module | Alerts and Notification Management-Fault notification, Alerts,Emergency Action/Procedure,Camera & Night vision and Day vision object detection | Frontend Team | 2026-01-24 | 2026-01-30 | Design/Development | 7 | Sprint 13 | Planned | Central alert orchestration for faults and visual detections.
GUI / Frontend Development | GCS Interface Module | Video Processing at GCS | Frontend Team | 2026-01-31 | 2026-02-06 | Design/Development | 7 | Sprint 14 | Planned | Real-time video decoding, stitching, overlay and analytics.
GUI / Frontend Development | GCS Interface Module | Pre-& Post Test of all the Peripherals for UGV Systems-PTZ Cameras,Motor & Its Parameters,Battery,GNSS | Frontend Team | 2026-02-07 | 2026-02-13 | Design/Development | 7 | Sprint 15 | Planned | Define and execute pre/post peripheral tests.
GUI / Frontend Development | GCS Interface Module | GO / NO GO decision -POST related requirements.(Payload- IRM, Motor, Engine Parameters & Other Parameters)-Pre & Post Test | Frontend Team | 2026-02-14 | 2026-02-20 | Design/Development | 7 | Sprint 16 | Planned | Automate GO/NO-GO checks based on POST results.
GUI / Frontend Development | GCS Interface Module | Return to Home-Upon System failures,Safety Return scenarios | Frontend Team | 2026-02-21 | 2026-02-27 | Design/Development | 7 | Sprint 17 | Planned | Implement safety RTH flows and abort conditions.
Firmware Development | Core Firmware | Mode Selection(CRC,TeleOperation,Autonomous,Follow Me),all mode status check | Sachin Kate, Mahadevi Biradar | 2025-11-22 | 2025-12-05 | Development/Integration | 14 | Sprint 4 | Planned | Develop and validate control modes and their status reporting.
Firmware Development | Core Firmware | Communucation & Networking -server creation ,connection established,process text message,send messages to clients,stop connection,check gps data(heading & location loss & update-update bms data,update ugv location,update counter) | Sachin Kate, Mahadevi Biradar | 2025-11-29 | 2025-12-12 | Development/Integration | 14 | Sprint 5 | Planned | Server-client comms, message handling, GPS/BMS updates and resilience.
Firmware Development | Core Firmware | connect to GPS,Get GPS Status-Stop -Request For Interruption ,update gps latitude and longitude | Sachin Kate, Mahadevi Biradar | 2025-12-06 | 2025-12-19 | Development/Integration | 14 | Sprint 6 | Planned | Integrate GPS, status management and interruption handling.
Firmware Development | Core Firmware | LMS Read-Connect,Get LMS Status,Stop LMS-Interruption & Stream Close | Sachin Kate, Mahadevi Biradar | 2025-12-13 | 2025-12-26 | Development/Integration | 14 | Sprint 7 | Planned | Implement LMS streaming, status checks and safe stop.
Firmware Development | Core Firmware | GamepadControls-Palco-Connect,Disconnect,Move While Stop ,Frame & Its Parameters,Command Codes,Payload Bytes,Checksum | Sachin Kate, Mahadevi Biradar | 2025-12-20 | 2026-01-02 | Development/Integration | 14 | Sprint 8 | Planned | Integrate gamepad control, framing, commands and checksums.
Firmware Development | Core Firmware | Follow Me-UWB Anchor & Tags | Sachin Kate, Mahadevi Biradar | 2025-12-27 | 2026-01-09 | Development/Integration | 14 | Sprint 9 | Planned | Implement UWB-based follow-me behavior and handling.
Firmware Development | Core Firmware | Update Satellite Number | Sachin Kate, Mahadevi Biradar | 2026-01-03 | 2026-01-16 | Development/Integration | 14 | Sprint 10 | Planned | Support satellite count updates and GNSS health.
Firmware Development | Core Firmware | LMS-Check ,Connect,Get KMS StatusUpdate LMS Data,Handle GCS command ,Object Identification-Find Closest Obstacle-Find Obstacle in FOV,Error in autonomy | Sachin Kate, Mahadevi Biradar | 2026-01-10 | 2026-01-23 | Development/Integration | 14 | Sprint 11 | Planned | LMS integration with object ID and autonomy error handling.
Firmware Development | Core Firmware | Handle Motor Driver Control | Sachin Kate, Mahadevi Biradar | 2026-01-17 | 2026-01-30 | Development/Integration | 14 | Sprint 12 | Planned | Motor driver commands, interlocks and safety controls.
Firmware Development | Core Firmware | Handle PTZ Camera & 6+ 1 Cameras (move camera Up,Down,Right,Left) | Sachin Kate, Mahadevi Biradar | 2026-01-24 | 2026-02-06 | Development/Integration | 14 | Sprint 13 | Planned | Camera control APIs and preset management for multiple cameras.
Firmware Development | Core Firmware | Curtis Control & its Parameter | Sachin Kate, Mahadevi Biradar | 2026-01-31 | 2026-02-13 | Development/Integration | 14 | Sprint 14 | Planned | Integrate and calibrate Curtis module parameters.
Firmware Development | Core Firmware | Autonomy-Calculate Distance,find closest obstacle | Sachin Kate, Mahadevi Biradar | 2026-02-07 | 2026-02-20 | Development/Integration | 14 | Sprint 15 | Planned | Autonomy algorithms for distance calc and obstacle selection.
Firmware Development | Core Firmware | Can Communication Establishment-Motor Controls-Reconnect CAN,Drive Forward,Change Interlock Status,Turn Sharp Right,Left,Stop UGV | Sachin Kate, Mahadevi Biradar | 2026-02-14 | 2026-02-27 | Development/Integration | 14 | Sprint 16 | Planned | CAN bus establishment and motor control command set.
Firmware Development | Core Firmware | Each Module Testing | Sachin Kate, Mahadevi Biradar | 2026-02-21 | 2026-03-06 | Development/Integration | 14 | Sprint 17 | Planned | Module-level unit testing and verification.
Firmware Development | Core Firmware | All Module integration | Sachin Kate, Mahadevi Biradar | 2026-02-28 | 2026-03-13 | Development/Integration | 14 | Sprint 18 | Planned | Integrate modules and verify interactions.
Firmware Development | Core Firmware | Final Code | Sachin Kate, Mahadevi Biradar | 2026-03-07 | 2026-03-20 | Development/Integration | 14 | Sprint 19 | Planned | Release candidate firmware build.
Firmware Development | Core Firmware | Field Test | Sachin Kate, Mahadevi Biradar | 2026-03-14 | 2026-03-27 | Development/Integration | 14 | Sprint 20 | Planned | On-field acceptance testing.
Firmware Development | Peripheral - Joysticks | Joysticks - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-03-21 | 2026-03-27 | Development/Integration | 7 | Sprint 21 | Planned | Joysticks technical spec review and requirements.
Firmware Development | Peripheral - Joysticks | Joysticks - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-03-28 | 2026-04-03 | Development/Integration | 7 | Sprint 22 | Planned | Develop and run trial code for Joysticks to validate interfaces.
Firmware Development | Peripheral - Joysticks | Joysticks - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-04 | 2026-04-10 | Development/Integration | 7 | Sprint 23 | Planned | Implement Joysticks code following IEEE standards.
Firmware Development | Peripheral - Joysticks | Joysticks - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Joysticks drivers into ROS2 nodes.
Firmware Development | Peripheral - Joysticks | Joysticks - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Joysticks code and prepare for integration.
Firmware Development | Peripheral - Camera Encoder | Camera Encoder - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Camera Encoder technical spec review and requirements.
Firmware Development | Peripheral - Camera Encoder | Camera Encoder - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Camera Encoder to validate interfaces.
Firmware Development | Peripheral - Camera Encoder | Camera Encoder - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Camera Encoder code following IEEE standards.
Firmware Development | Peripheral - Camera Encoder | Camera Encoder - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Camera Encoder drivers into ROS2 nodes.
Firmware Development | Peripheral - Camera Encoder | Camera Encoder - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Camera Encoder code and prepare for integration.
Firmware Development | Peripheral - PTZ Camera | PTZ Camera - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | PTZ Camera technical spec review and requirements.
Firmware Development | Peripheral - PTZ Camera | PTZ Camera - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for PTZ Camera to validate interfaces.
Firmware Development | Peripheral - PTZ Camera | PTZ Camera - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement PTZ Camera code following IEEE standards.
Firmware Development | Peripheral - PTZ Camera | PTZ Camera - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate PTZ Camera drivers into ROS2 nodes.
Firmware Development | Peripheral - PTZ Camera | PTZ Camera - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize PTZ Camera code and prepare for integration.
Firmware Development | Peripheral - Adam Module | Adam Module - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Adam Module technical spec review and requirements.
Firmware Development | Peripheral - Adam Module | Adam Module - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Adam Module to validate interfaces.
Firmware Development | Peripheral - Adam Module | Adam Module - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Adam Module code following IEEE standards.
Firmware Development | Peripheral - Adam Module | Adam Module - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Adam Module drivers into ROS2 nodes.
Firmware Development | Peripheral - Adam Module | Adam Module - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Adam Module code and prepare for integration.
Firmware Development | Peripheral - GPS Module | GPS Module - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | GPS Module technical spec review and requirements.
Firmware Development | Peripheral - GPS Module | GPS Module - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for GPS Module to validate interfaces.
Firmware Development | Peripheral - GPS Module | GPS Module - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement GPS Module code following IEEE standards.
Firmware Development | Peripheral - GPS Module | GPS Module - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate GPS Module drivers into ROS2 nodes.
Firmware Development | Peripheral - GPS Module | GPS Module - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize GPS Module code and prepare for integration.
Firmware Development | Peripheral - GNSS Module | GNSS Module - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | GNSS Module technical spec review and requirements.
Firmware Development | Peripheral - GNSS Module | GNSS Module - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for GNSS Module to validate interfaces.
Firmware Development | Peripheral - GNSS Module | GNSS Module - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement GNSS Module code following IEEE standards.
Firmware Development | Peripheral - GNSS Module | GNSS Module - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate GNSS Module drivers into ROS2 nodes.
Firmware Development | Peripheral - GNSS Module | GNSS Module - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize GNSS Module code and prepare for integration.
Firmware Development | Peripheral - Motor | Motor - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Motor technical spec review and requirements.
Firmware Development | Peripheral - Motor | Motor - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Motor to validate interfaces.
Firmware Development | Peripheral - Motor | Motor - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Motor code following IEEE standards.
Firmware Development | Peripheral - Motor | Motor - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Motor drivers into ROS2 nodes.
Firmware Development | Peripheral - Motor | Motor - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Motor code and prepare for integration.
Firmware Development | Peripheral - Motor Driver | Motor Driver - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Motor Driver technical spec review and requirements.
Firmware Development | Peripheral - Motor Driver | Motor Driver - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Motor Driver to validate interfaces.
Firmware Development | Peripheral - Motor Driver | Motor Driver - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Motor Driver code following IEEE standards.
Firmware Development | Peripheral - Motor Driver | Motor Driver - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Motor Driver drivers into ROS2 nodes.
Firmware Development | Peripheral - Motor Driver | Motor Driver - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Motor Driver code and prepare for integration.
Firmware Development | Peripheral - Camera Module | Camera Module - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Camera Module technical spec review and requirements.
Firmware Development | Peripheral - Camera Module | Camera Module - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Camera Module to validate interfaces.
Firmware Development | Peripheral - Camera Module | Camera Module - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Camera Module code following IEEE standards.
Firmware Development | Peripheral - Camera Module | Camera Module - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Camera Module drivers into ROS2 nodes.
Firmware Development | Peripheral - Camera Module | Camera Module - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Camera Module code and prepare for integration.
Firmware Development | Peripheral - Radio Module | Radio Module - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Radio Module technical spec review and requirements.
Firmware Development | Peripheral - Radio Module | Radio Module - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for Radio Module to validate interfaces.
Firmware Development | Peripheral - Radio Module | Radio Module - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement Radio Module code following IEEE standards.
Firmware Development | Peripheral - Radio Module | Radio Module - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate Radio Module drivers into ROS2 nodes.
Firmware Development | Peripheral - Radio Module | Radio Module - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize Radio Module code and prepare for integration.
Firmware Development | Peripheral - 3D LIDAR | 3D LIDAR - Technical data Study | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | 3D LIDAR technical spec review and requirements.
Firmware Development | Peripheral - 3D LIDAR | 3D LIDAR - Trial Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Develop and run trial code for 3D LIDAR to validate interfaces.
Firmware Development | Peripheral - 3D LIDAR | 3D LIDAR - Code as per IEEE Standard | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Implement 3D LIDAR code following IEEE standards.
Firmware Development | Peripheral - 3D LIDAR | 3D LIDAR - Code as per ROS2 | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Port/integrate 3D LIDAR drivers into ROS2 nodes.
Firmware Development | Peripheral - 3D LIDAR | 3D LIDAR - Final Code | Sachin Kate, Mahadevi Biradar | 2026-04-11 | 2026-04-17 | Development/Integration | 7 | Sprint 24 | Planned | Finalize 3D LIDAR code and prepare for integration.
Hardware & Peripheral Testing | Validation & Field Tests | Hardware Test Bench Setup | Hardware Team, QA Team | 2026-01-17 | 2026-01-30 | Validation/Testing | 14 | Sprint 12 | Planned | Prepare test bench and required fixtures.
Hardware & Peripheral Testing | Validation & Field Tests | Pre-Integration Peripheral Tests | Hardware Team, QA Team | 2026-01-24 | 2026-02-06 | Validation/Testing | 14 | Sprint 13 | Planned | Run pre-integration tests for PTZ, motors, battery, GNSS.
Hardware & Peripheral Testing | Validation & Field Tests | Sensor Calibration & Validation | Hardware Team, QA Team | 2026-01-31 | 2026-02-13 | Validation/Testing | 14 | Sprint 14 | Planned | Calibrate LiDAR, IMU, GNSS and validate outputs.
Hardware & Peripheral Testing | Validation & Field Tests | Environmental Stress Testing (Thermal/Vibration) | Hardware Team, QA Team | 2026-02-07 | 2026-02-20 | Validation/Testing | 14 | Sprint 15 | Planned | Thermal and vibration stress tests.
Hardware & Peripheral Testing | Validation & Field Tests | EMI/EMC Testing | Hardware Team, QA Team | 2026-02-14 | 2026-02-27 | Validation/Testing | 14 | Sprint 16 | Planned | Conduct EMI/EMC testing as per standards.
Hardware & Peripheral Testing | Validation & Field Tests | Integration with Firmware | Hardware Team, QA Team | 2026-02-21 | 2026-03-06 | Validation/Testing | 14 | Sprint 17 | Planned | Validate hardware after firmware integration.
Hardware & Peripheral Testing | Validation & Field Tests | Field Integration Testing | Hardware Team, QA Team | 2026-02-28 | 2026-03-13 | Validation/Testing | 14 | Sprint 18 | Planned | Full system field tests and performance validation.
Quality Assurance (QA) | Testing & Validation | Test Plan Preparation | QA Team | 2026-02-07 | 2026-02-20 | Testing/Delivery | 14 | Sprint 15 | Planned | Create QA test plan, test cases and acceptance criteria.
Quality Assurance (QA) | Testing & Validation | Functional & Regression Testing | QA Team | 2026-02-14 | 2026-02-27 | Testing/Delivery | 14 | Sprint 16 | Planned | Execute functional and regression test suites.
Quality Assurance (QA) | Testing & Validation | Bug Triaging & Fix Verification | QA Team | 2026-02-21 | 2026-03-06 | Testing/Delivery | 14 | Sprint 17 | Planned | Triage issues and verify fixes across sprints.
Quality Assurance (QA) | Testing & Validation | Final QA Sign-off | QA Team | 2026-02-28 | 2026-03-13 | Testing/Delivery | 14 | Sprint 18 | Planned | Prepare QA reports and sign-off documentation.
Project Management (PMO) | Management | Project Kick-off & Resource Allocation | PMO Team | 2025-11-01 | 2025-11-14 | Continuous | 14 | Sprint 1 | Planned | Initiate project and allocate resources.
Project Management (PMO) | Management | Weekly Sprint Reviews | PMO Team | 2025-11-01 | 2026-04-17 | Continuous | 168 | Sprint 1 | Planned | Weekly progress, impediment removal and stakeholder updates.
Project Management (PMO) | Management | Mid-Project Review | PMO Team | 2026-01-17 | 2026-01-30 | Review | 14 | Sprint 12 | Planned | Assess progress and replan.
Project Management (PMO) | Management | Final Delivery & Handover | PMO Team | 2026-04-04 | 2026-04-17 | Delivery | 14 | Sprint 23 | Planned | Final handover, documentation and training.