## Estimates
Function | Req. Tag | Requirements | Status | Req. Clarity | Effort (in hrs) | Effort (in Days) | Remarks | Detailed Analysis | Start Date | End Date
Authentication & Authorization Management | GCSAA1 | Authentication for System Configuration (Admin) | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
Authentication & Authorization Management | GCSAA2 | Authentication for System Maintenance | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
Authentication & Authorization Management | GCSAA3 | Operator authentication | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
Map Data Preparation | GCSMD1 | Preload DSM series Map data | NOT STARTED | 20% | 200 | 25 |  | 1. More details needed on DSM maps | TBD | TBD
Map Data Preparation | GCSMD2 | Map display | NOT STARTED | 90% | 20 | 2.5 |  |  | TBD | TBD
Data Exchange between GCS and GDT – RF | GCSGT1 | Bi-directional comm. with IP Mesh Radio Ground Based Comm. Terminal | NOT STARTED | 70% | 40 | 5 |  |  | TBD | TBD
Data Exchange between GCS and GDT – RF | GCSGT2 | Data & Video communication channels | NOT STARTED | 100% | 40 | 5 |  |  | TBD | TBD
UI Panels for Mission Planning | GCSMP1 | 2D map display – DSM Maps | NOT STARTED | 50% | 80 | 10 |  | 1. More details needed on DSM maps | TBD | TBD
UI Panels for Mission Planning | GCSMP2 | Planning facility in the Map Mode(Mission Programming Planning ) | NOT STARTED | 100% | 80 | 10 |  |  | TBD | TBD
UI Panels for Mission Planning | GCSMP3 | Real-time path plan alteration by operator | NOT STARTED | 100% | 80 | 10 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP1 | Map View Panels | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP2 | Mission plan display | NOT STARTED | 100% | 40 | 5 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP3 | Mission plan modification | NOT STARTED | 100% | 40 | 5 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP4 | Operations Panels | NOT STARTED | 40% | 45 | 5.625 |  | 1. Please list down the appropriate mission parameters | TBD | TBD
UI Panels for GCS Operations | GCSOP5 | Power-On Self-Test (POST) | NOT STARTED | 70% | 80 | 10 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP6 | Camera payload video stream | NOT STARTED | 70% | 20 | 2.5 |  | 1. Camera yet to be selected | TBD | TBD
UI Panels for GCS Operations | GCSOP7 | Emergency Management View | NOT STARTED | 50% | 25 | 3.125 |  |  | TBD | TBD
UI Panels for GCS Operations | GCSOP8 | EO sight | NOT STARTED | 70% | 30 | 3.75 |  |  | TBD | TBD
Notification Messages | GCSNM1 | Display of Notification | NOT STARTED | 50% | 40 | 5 |  | 1. What are the system health parameters to be displayed? | TBD | TBD
Notification Messages | GCSNM2 | Emergency Situation Notification | NOT STARTED | 70% | 40 | 5 |  |  | TBD | TBD
Notification Messages | GCSNM3 | Geo-Fence breach Notification | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
Notification Messages | GCSNM4 | Notification related to Em.Procedure execution by Peripheral | NOT STARTED | 20% | 40 | 5 |  | 1. Need more input on Emergency management procedure | TBD | TBD
Alert Pop-Ups | GCSAP1 | Alerts display if targets / objects detected | NOT STARTED | 60% | 80 | 10 |  | 1. Is this object detection requirement in video? | TBD | TBD
Alert Pop-Ups | GCSAP2 | Alerts for system health | NOT STARTED | 40% | 30 | 3.75 |  | 1. Need more clarity on the health threshold requirements | TBD | TBD
Alert Pop-Ups | GCSAP3 | Alerts for terrain avoidance | NOT STARTED | 100% | 25 | 3.125 |  |  | TBD | TBD
Alert Pop-Ups | GCSAP4 | Alerts for non-feasible Mission plan | NOT STARTED | 70% | 50 | 6.25 |  | 1. What are the criteria for non-feasible mission plan? | TBD | TBD
Alert Pop-Ups | GCSAP5 | Alerts for impending Geo-fence breach | NOT STARTED | 100% | 10 | 1.25 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN1 | Transmitting operator’s commands from GCS to UGV Controller | NOT STARTED | 50% | 50 | 6.25 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN2 | Way-point Navigation commands from GCS to UGV Controller | NOT STARTED | 70% | 40 | 5 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN3 | Command from GCS for RTH | NOT STARTED | 40% | 40 | 5 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN4 | Remote Handset control mode display | NOT STARTED | 80% | 20 | 2.5 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN5 | RF Downlink (AV to GCS) - Data | NOT STARTED | 80% | 40 | 5 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN6 | RF Downlink (UGV to GCS) -Insights | NOT STARTED | 60% | 40 | 5 |  | 1. What are the insights? | TBD | TBD
Communication & Networking Protocols | GCSCN7 | RF Downlink (UGV to GCS)- Video | NOT STARTED | 90% | 50 | 6.25 |  |  | TBD | TBD
Communication & Networking Protocols | GCSCN8 | RF Uplink (GCS to UGV)- Commands | NOT STARTED | 90% | 80 | 10 |  | Need all the command list | TBD | TBD
Communication & Networking Protocols | GCSCN9 | RF Uplink (GCS to UGV)- Mission File | NOT STARTED | 100% | 25 | 3.125 |  |  | TBD | TBD
Data Storage & Back Up | GCSDS1 | Encrypted data storage at GCS | NOT STARTED | 80% | 80 | 10 |  |  | TBD | TBD
Data Storage & Back Up | GCSDS2 | GCS to retain N mission log data | NOT STARTED | 80% | 40 | 5 |  |  | TBD | TBD
Video Recording / Image Snapshot storage | GCSVS1 | Video Recording in GCS | NOT STARTED | 100% | 50 | 6.25 |  |  | TBD | TBD
Video Recording / Image Snapshot storage | GCSVS2 | Alert pop up for Video data back-up or flush-out | NOT STARTED | 100% | 10 | 1.25 |  |  | TBD | TBD
System Health Assessment (Diagnostics Management) | GCSDM1 | Diagnostics | NOT STARTED | 50% | 60 | 7.5 |  | 1. Need improvement in Diagnostics data Requirements | TBD | TBD
Fault Management | GCSFM1 | Integrated with System Health Assessment (Diagnostics) | NOT STARTED | 50% | 60 | 7.5 |  | 1. Need improvement in Diagnostics data Requirements | TBD | TBD
Fault Management | GCSFM2 | Fault prioritization | NOT STARTED | 50% | 40 | 5 |  | 1. Fault Management and Fault Prioritization based on Severity – needs more clarity | TBD | TBD
Fault Management | GCSFM3 | Fault Information to be integrated with Emergency Management | NOT STARTED | 60% | 50 | 6.25 |  |  | TBD | TBD
Emergency Management System | GCSEM1 | Emergency Management Engine | NOT STARTED | 50% | 30 | 3.75 |  | 1. Rule based Emergency Procedure – needs more clarity | TBD | TBD
Emergency Management System | GCSEM2 | Emergency Management Decision support | NOT STARTED | 30% | 30 | 3.75 |  | 1. Rule based Emergency Procedure – needs more clarity | TBD | TBD
Emergency Management System | GCSEM3 | In case of GPS loss, RTH | NOT STARTED | 90% | 25 | 3.125 |  |  | TBD | TBD
Emergency Management System | GCSEM4 | Low Battery | NOT STARTED | 100% | 15 | 1.875 |  |  | TBD | TBD
Emergency Management System | GCSEM5 | Geo-fence breach | NOT STARTED | 100% | 15 | 1.875 |  |  | TBD | TBD
Emergency Management System | GCSEM6 | Minor fault | NOT STARTED | 50% | 30 | 3.75 |  | 1. Minor faults to be detailed | TBD | TBD
Emergency Management System | GCSEM7 | Temporary Comm. Loss | NOT STARTED | 60% | 20 | 2.5 |  |  | TBD | TBD
Emergency Management System | GCSEM8 | Persistent Comm. Loss | NOT STARTED | 100% | 20 | 2.5 |  |  | TBD | TBD
Emergency Management System | GCSEM9 | Persistent Comm. Loss, accompanied by high winds and hostile weather | NOT STARTED | 80% | 40 | 5 |  | Do we have the wind sensors integrated? | TBD | TBD
Emergency Management System | GCSEM10 | Hostile weather situations | NOT STARTED | 80% | 20 | 2.5 |  |  | TBD | TBD
Alerts and Notification Management | GCSAN1 | Alerts and Notification related to system health | NOT STARTED | 50% | 50 | 6.25 |  | 1. Fault notification, Alerts requirements needs to be improved | TBD | TBD
Alerts and Notification Management | GCSAN2 | GCS advisory for emergency procedure | NOT STARTED | 30% | 40 | 5 |  | 1. Emergency Action/Procedure requirement needs to be improved | TBD | TBD
Alerts and Notification Management | GCSAN3 | GCS to notify if Autopilot triggers Emergency Management | NOT STARTED | 80% | 40 | 5 |  | 1. Emergency Action/Procedure requirement needs to be improved | TBD | TBD
Alerts and Notification Management | GCSAN4 | GCS to notify if object(s) gets detected in video feed | NOT STARTED | 60% | NA |  |  | 1.Camera not finalised yet 2. How object detected. both Night vision and Day vision object detection? | TBD | TBD
Video Processing at GCS | GCSVP1 | Reception of video feed from UGV | NOT STARTED | 80% | 40 | 5 |  | 1.Camera not finalised yet | TBD | TBD
Video Processing at GCS | GCSVP1 | Target information capture | NOT STARTED | 25% | 40 | 5 |  | 1.Camera not finalised yet 2. How Distance captured in Video Processing? | TBD | TBD
Video Processing at GCS | GCSVP1 | Video Feed sequence storage | NOT STARTED | 80% | 40 | 5 |  | 1.Camera not finalised yet | TBD | TBD
Video Processing at GCS | GCSVP1 | Video frame snapshots | NOT STARTED | 80% | 40 | 5 |  | 1.Camera not finalised yet | TBD | TBD
Pre-& Post Test of all the Peripherals for UGV Systems | GCSAT1 | Standalone Test Tool at GCS for testing Payload (IRM) | NOT STARTED | 80% | 25 | 3.125 |  | 1.PTZ camera not finalised | TBD | TBD
Pre-& Post Test of all the Peripherals for UGV Systems | GCSAT2 | Standalone Test Tool at GCS for testing Motors | NOT STARTED | 80% | 25 | 3.125 |  | 1.Motor not finalised yet 2. Need to details of Motor parameters | TBD | TBD
Pre-& Post Test of all the Peripherals for UGV Systems | GCSAT3 | Standalone Test tool at GCS for Engine Testing | NOT STARTED | 80% | 25 | 3.125 |  | 1.Battery details yet to be provided | TBD | TBD
Pre-& Post Test of all the Peripherals for UGV Systems | GCSAT4 | Standalone test tool at GCS for camera | NOT STARTED | 80% | 25 | 3.125 |  | 1.Camera not finalised yet | TBD | TBD
Pre-& Post Test of all the Peripherals for UGV Systems | GCSAT5 | Standalone test tool for GNSS | NOT STARTED | 80% | 25 | 3.125 |  | 1. New GNSS details yet to be shared/Analysed | TBD | TBD
GO / NO GO decision | GCSGN1 | Go / No Go decision | NOT STARTED | 50% | 60 | 7.5 |  | 1. Need more clarity on POST related requirements.(Payload- IRM, motor, Engine Parameters) 2. Checks needed for Post and pre tests not Provided. | TBD | TBD
Return to Home | GCSSL1 | Marking pre-determined safe spots | NOT STARTED | 100% | 30 | 3.75 |  |  | TBD | TBD
Return to Home | GCSSL1 | Marking per-determined safe spots | NOT STARTED | 100% | 40 | 5 |  |  | TBD | TBD
Return to Home | GCSSL2 | Parameters to be monitored at GCS | NOT STARTED | 60% | 100 | 12.5 |  | 1. System failures not provided as requirement | TBD | TBD
Return to Home | GCSSL3 | Operator to command for Safely Return to Home | NOT STARTED | 80% | 60 | 7.5 |  | 1. Requirements missing for Safety Return scenarios | TBD | TBD
Other Requirements | Others | Integration of Telescopic Mast | NOT STARTED | 50% | 60 | 7.5 |  | 1. Requirements yet to be added | TBD | TBD
Other Requirements | Others | Integration of Laser Range Finder (LRF) | NOT STARTED | 80% | 60 | 7.5 |  | 1. Requirements yet to be added | TBD | TBD
Other Requirements | Others | Integration of Audio Recorders | NOT STARTED | 80% | 60 | 7.5 |  | 1. Requirements yet to be added | TBD | TBD
Other Requirements | Others | Digital Recording Device | NOT STARTED | 80% | 60 | 7.5 |  | 1. Requirements yet to be added | TBD | TBD
Other Requirements | Others | Follow me Operations | NOT STARTED | 20% | 120 | 15 |  | 1. The Device is not selected yet for this operation 2. No Requirements formed yet for this operation | TBD | TBD
|  |  |  | Total Effort-Days | 3320 | 415

## Standards
| IEEE-1012 – Software Standard for Verification and Validation | IEEE-12207- System and Software Engineering Life cycle Process
Clause Number | Standards to be tested | Clause Number | Process Name
5.1.1 | Management of V&V Activity | 6 | System Life Cycle Processes
| Software Verification and Validation plan Generation | 6.1 | Agreement Processes
| Baseline Change Management | 6.1.1 | Acquisition Process
| Management review of V&V | 6.1.2 | Supply Process
| Management and Technical Review support | 6.2 | Organizational Project-Enabling
| Interface with organisational and support process | 6.2.1 | Life Cycle Model Management Process
|  | 6.2.2 | Infrastructure Management Process
5.2.1 | Acquistion support V&V Activity | 6.2.3 | Project Portfolio Management Process
| Scoping the V&V Effort | 6.2.4 | Human Resource Management Process
| Planning the Interface between V&V Effort and Supplier | 6.2.5 | Quality Management Process
| System Requirement Review | 6.3 | Project Processes
|  | 6.3.1 | Project Planning Process
5.3.1 | Planning V&V Activity | 6.3.2 | Project Assessment and Control Process
| Planning the Interface between V&V Effort and Supplier | 6.3.3 | Decision Management Process
| Contract Verification | 6.3.4 | Risk Management Process
|  | 6.3.5 | Configuration Management Process
5.4.1 | Concept V&V Activity | 6.3.6 | Information Management Process
| Concept Documentation Evaluation | 6.3.7 | Measurement Process
| Criticality Analysis | 6.4 | Technical Processes
| Hardware/Software User Requirements | 6.4.1 | Stakeholder Requirements Definition
| Traceability Analysis | 6.4.2 | System Requirements Analysis
| Hazard Analysis | 6.4.3 | System Architectural Design
| Risk Analysis | 6.4.4 | Implementation Process
|  | 6.4.5 | System Integration Process
5.4.2 | Requirement V&V Activity | 6.4.6 | System Qualification Testing Process
| Traceability Analysis | 6.4.7 | Software Installation
| Software Requirements Evaluation | 6.4.8 | Software Acceptance Support
| Interface Analysis | 6.4.9 | Software Operation Process
| Criticality Analysis | 6.4.10 | Software Maintenance Process
| System V&V Test Plan | 6.4.11 | Software Disposal Process
| Acceptance V&V Test Plan Generation and Verification | 7 | Software Life Cycle Processes
| Configuration Management Assessment | 7.1 | Software Implementation Processes
| Hazard Analysis | 7.1.1 | Software Implementation Process
| Risk Analysis | 7.1.2 | Software Requirements Analysis Process
|  | 7.1.3 | Software Architectural Design Process
5.4.3 | Design V&V Activity | 7.1.4 | Software Detailed Design Process
| Traceability Analysis | 7.1.5 | Software Construction Process
| Software Design Evaluation | 7.1.6 | Software Integration Process
| Interface Analysis | 7.1.7 | Software Qualification Testing Process
| Criticality Analysis | 7.2 | Software Support Processes
| Component V&V test plan Generation and Verification | 7.2.1 | Software Documentation Management
| Integration V&V Test Plan Generation and Verification | 7.2.2 | Software Configuration Management
| V&V Test Design Generation and Verification | 7.2.3 | Software Quality Assurance Process
| Hazard Analysis | 7.2.4 | Software Verification Process
| Risk Analysis | 7.2.5 | Software Validation Process
|  | 7.2.6 | Software Review Process
5.4.4 | Implementation V&V Activity | 7.2.7 | Software Audit Process
| Traceability Analysis | 7.2.8 | Software Problem Resolution Process
| Source Code and Source Code Documentation Evaluation | 7.3 | Software Reuse Processes
| Interface Analysis | 7.3.1 | Domain Engineering Process
| Criticality Analysis | 7.3.2 | Reuse Asset Management Process
| V&V Test case Generation and Verification | 7.3.3 | Reuse Program Management Process
V&V Test Procedure Generation and Verification
Component V&V test execution and Verification
Hazard Analysis
Risk Analysis
5.4.5 | Test V&V Activity
Traceability Analysis
Acceptance V&V Test Procedure Generation and Verification
Integration V&V test Execution and Verification
System V&V Test Execution and Verification
Acceptance V&V Test Execution and Verification
Hazard Analysis
Risk Analysis
5.4.6 | Installation and Chechout V&V Activity
Installation Configuration Audit
Installation checkout
Hazard Analysis
Risk Analysis
V&V Final Report Generation